# TEACHING & RESEARCH DESIGN

## SCENARIO 2 - GLOBAL TEAM, SHIFTING REQUIREMENTS

### THE STORY

LearnLoop is a startup that just raised 3.2M EUR to build an AI-powered adaptive learning platform for universities. 12 people, three cities, very different skill sets:

- Amsterdam (UTC+1) – 4 people:

Product managers, UX designers, 1 frontend developer

Strength: user research, product vision, GDPR knowledge

Weakness: no ML or backend expertise

- Bangalore (UTC+5:30) - 5 people:

Backend engineers, ML engineers, 1 DevOps engineer

Strength: recommendation systems, scalable infrastructure

Weakness: no direct contact with end users or customers

- Austin (UTC-6) - 3 people:

Business development, data analyst, customer success

Strength: weekly calls with the pilot customer (University of Texas)

Weakness: no technical or product background

Timezone reality:

Amsterdam <-> Bangalore: 4.5h gap - small morning overlap only

Amsterdam <-> Austin:    7h gap   - small evening overlap only

Bangalore <-> Austin:    11.5h gap - nearly zero overlap

The first pilot customer wants a working MVP (Minimum Viable Product) in 9 months.

After the first stakeholder workshops, three problems surface immediately:

- Nobody at the university agrees on what the platform should do.

IT wants LMS integration. Professors want content control.

Students want to see why a recommendation was made.

Legal wants FERPA (Family Educational Rights and Privacy Act)

compliance before any student data is processed.

- Austin collects new requirements every week in customer calls,

but there is no process to pass them to Amsterdam or Bangalore.

- Bangalore has already started building the recommendation engine -

but Amsterdam has not yet decided what data the platform will collect.

Two engineers are frustrated because they keep receiving design mockups

that are architecturally impossible to implement.

The CEO is optimistic. The team is not.

### TASK 1 - ANALYSE

- Which Scrum elements create specific problems here? (Bullets points are fine)

| Scrum Element | Still works? | Why / Why not? |
| --- | --- | --- |
| 2-week sprints | Partially | Still useful for incremental delivery, but coordination across three time zones slows feedback and decision-making. |
| Definition of Done | Needs expansion | Features cannot be considered done unless product, technical, and legal requirements are aligned. A feature that works technically but violates FERPA is not done. |
| Backlog prioritization | Creates challenges | New requirements arrive weekly from Austin, causing frequent reprioritization and potential confusion across locations. |
| Sprint Review Demo | Partially | Reviews remain valuable, but stakeholders already disagree on product goals. Reviews may generate even more conflicting requirements. |
| Velocity tracking | Less reliable | Blockers caused by legal approvals, cross-team dependencies, and requirement uncertainty can reduce velocity without reflecting team performance. |

Additional problems:

- Customer knowledge is concentrated in Austin.

- Technical decisions are being made before product requirements are finalized.

- Time-zone separation slows conflict resolution.

- No clear ownership for requirement flow between locations.

### TASK 2 - DECIDE

Three situations. For each: pick one option and justify your choice.

"We would do both" is not an answer.

SITUATION A - WHOSE DESIGN WINS?

Amsterdam has designed a user interface that requires real-time

personalisation data streamed from the backend.

Bangalore says this is technically impossible with the current

architecture - a full redesign would take 3 months.

You have 9 months until the MVP deadline.

You cannot do a 3-month redesign AND build all features in time.

You have three options:

(1) Amsterdam adapts the design to fit the current architecture.

Risk: the user experience becomes significantly worse.

(2) Bangalore does the redesign. Sprint 1-6 produce almost nothing

visible, putting the 9-month deadline at serious risk.

(3) Ship the MVP with the weaker UX (option 1), then redesign

after the pilot customer has seen it.

- Which do you choose?

Option 3: Ship the MVP with the weaker UX, then redesign after the pilot.

Why?

The startup has a fixed 9-month deadline and needs feedback from a real university. A 3-month architectural redesign consumes one-third of the available schedule before the MVP exists. The pilot's purpose is learning what users actually need, so it is better to deliver a functional product with compromises than risk missing the pilot entirely.

- Who has the authority to make this call - and what happens if

The Product Owner (or Head of Product) should make the final decision because this is fundamentally a business trade-off between user experience and delivery risk.

- Amsterdam and Bangalore cannot agree?

Escalate to the Product Owner with:

- UX impact estimate from Amsterdam

- Technical cost estimate from Bangalore

- Deadline impact analysis

The Product Owner makes the final decision based on business priorities rather than team preference.

SITUATION B - THE ONLY MEETING SLOT

You have exactly one 90-minute slot per week where all three teams

can meet synchronously (15:00-16:30 Amsterdam time).

This week you have three agenda items that are all critical:

(1) Finalise the data model - Bangalore is blocked without this.

(2) Review 6 new requirements from the university - Austin needs

a decision before the next customer call on Friday.

(3) Resolve the Amsterdam/Bangalore architecture conflict

from Situation A - it has been unresolved for 2 weeks.

You can cover two of the three properly in 90 minutes.

- Which item do you drop from the live meeting?

Drop Item 2: Review the six new university requirements.

Why?

Items 1 and 3 are active blockers:

- Bangalore cannot proceed without the data model.

- The architecture conflict has already delayed work for two weeks.

The new requirements are important, but they are not currently stopping development.

- How do you handle it differently so it does not stall the team?

Use an asynchronous process:

- Austin documents requirements in a shared backlog.

- Amsterdam reviews them before the next customer call.

- Questions are collected asynchronously through project-management tools.

- Only unresolved high-risk requirements are brought to the next live meeting.

This preserves meeting time for urgent cross-team decisions.

SITUATION C - THE LEGAL BLOCKER

Halfway through Sprint 3, Austin calls with urgent news:

the University of Texas legal team has blocked all student data

collection until a FERPA (Family Educational Rights and Privacy Act)

compliance agreement is signed. Signing takes 6-8 weeks minimum.

Bangalore is currently mid-sprint, building the recommendation engine

that depends entirely on that student data.

You have three options:

(1) Stop Bangalore's work immediately. Wait 6-8 weeks.

Cost: 6-8 weeks of lost development time and team frustration.

(2) Continue building the engine on synthetic (fake) data.

Risk: the engine may need significant rework once real data arrives

and behaves differently than expected.

(3) Redirect Bangalore to a different part of the product

(e.g., the LMS integration) while legal is resolved.

Risk: context switching costs and the engine falls further behind.

- Which option do you choose?

Option 3: Redirect Bangalore to another part of the product.

### Why?

Option 1 wastes 6–8 weeks of expensive engineering capacity.

Option 2 risks building a recommendation engine around assumptions that may not match real student data.

By shifting work toward LMS integration, APIs, infrastructure, authentication, monitoring, or other backend capabilities, the team continues creating value while legal approval progresses.

- How do you communicate this decision to the Bangalore team?

Explain that the pause is caused by an external legal dependency, not by a failure of their work.

### TASK 3 - REFLECT

In 2-3 sentences:

- Which situation revealed the biggest structural weakness in how LearnLoop is organised?

Situation B revealed the biggest structural weakness. Critical information is trapped within individual locations—Austin talks to customers, Amsterdam owns product decisions, and Bangalore builds the system—yet there is no reliable process for sharing information between them. As a result, important decisions depend on a single weekly meeting, creating bottlenecks and delays.

- What would need to change in the company to make that situation not happen in the first place?

LearnLoop needs a clearer product governance structure, including a dedicated Product Owner, a shared and continuously updated backlog, and documented requirements accessible to all teams. Customer feedback should be communicated asynchronously throughout the week instead of waiting for one cross-timezone meeting, reducing dependency on scarce synchronous communication.

### AI ANALYSIS

Paste into ChatGPT or Claude:

"We are software engineering students. We made process decisions for

LearnLoop, a startup with teams in Amsterdam, Bangalore, and Austin.

These were our choices: [paste your Task 2 answers].

Challenge our decisions. For each choice, what is the strongest argument

for the option we did NOT pick? Be specific - focus on team dynamics

and the 9-month deadline pressure."

Then write 2-3 sentences:

- Did the AI make a valid counterargument you had not considered? Or did it ignore a constraint that made your option the only realistic one?

The strongest counterargument is for Situation C. It highlights that the recommendation engine is the product's main competitive advantage, and delaying ML work entirely could create a greater risk to the 9-month deadline than controlled rework from synthetic data. That is a trade-off many teams underestimate.

- Would you change any of your three choices?

I would keep Situation A and Situation B because unresolved blockers still pose the biggest immediate threat to delivery. However, I would seriously consider changing Situation C from Option 3 to Option 2, allowing Bangalore to continue developing ML infrastructure with synthetic data while clearly accepting the possibility of future adjustments once FERPA approval is completed.