# TEACHING & RESEARCH DESIGN

## SCENARIO 2 - GLOBAL TEAM, SHIFTING REQUIREMENTS

### THE STORY

LearnLoop is a startup that just raised 3.2M EUR to build an AI-powered adaptive learning platform for universities. 12 people, three cities, very different skill sets:

- Amsterdam (UTC+1) – 4 people:

Product managers, UX designers, 1 frontend developer

Strength: user research, product vision, GDPR knowledge

Weakness: no ML or backend expertise

- Bangalore (UTC+5:30) - 5 people:

Backend engineers, ML engineers, 1 DevOps engineer

Strength: recommendation systems, scalable infrastructure

Weakness: no direct contact with end users or customers

- Austin (UTC-6) - 3 people:

Business development, data analyst, customer success

Strength: weekly calls with the pilot customer (University of Texas)

Weakness: no technical or product background

Timezone reality:

Amsterdam <-> Bangalore: 4.5h gap - small morning overlap only

Amsterdam <-> Austin:    7h gap   - small evening overlap only

Bangalore <-> Austin:    11.5h gap - nearly zero overlap

The first pilot customer wants a working MVP (Minimum Viable Product) in 9 months.

After the first stakeholder workshops, three problems surface immediately:

- Nobody at the university agrees on what the platform should do.

IT wants LMS integration. Professors want content control.

Students want to see why a recommendation was made.

Legal wants FERPA (Family Educational Rights and Privacy Act)

compliance before any student data is processed.

- Austin collects new requirements every week in customer calls,

but there is no process to pass them to Amsterdam or Bangalore.

- Bangalore has already started building the recommendation engine -

but Amsterdam has not yet decided what data the platform will collect.

Two engineers are frustrated because they keep receiving design mockups

that are architecturally impossible to implement.

The CEO is optimistic. The team is not.

### TASK 1 - ANALYSE

- Which Scrum elements create specific problems here? (Bullets points are fine)

| Scrum Element | Still works? | Why / Why not? |
| --- | --- | --- |
| 2 – week sprints | No | Teams are not synchronized; with significant time zone differences, effective collaboration and continuous feedback during sprints are challenging. |
| Definition of Done | No. | Inconsistent expectations among teams lead to issues in delivering a coherent product, particularly since requirements differ from one location to another. |
| Backlog prioritization | No. | Without a unified understanding of priorities among teams and stakeholders, competing demands lead to confusion and inefficiency. |
| Sprint Review Demo | No. | Diverse stakeholder expectations mean reviews may not cover key priorities or may fail to align the teams on user needs. |
| Velocity tracking | No. | Different teams have different focuses; velocity may not represent meaningful progress if work across teams lacks synergy. |

### TASK 2 - DECIDE

Three situations. For each: pick one option and justify your choice.

"We would do both" is not an answer.

SITUATION A - WHOSE DESIGN WINS?

Amsterdam has designed a user interface that requires real-time

personalisation data streamed from the backend.

Bangalore says this is technically impossible with the current

architecture - a full redesign would take 3 months.

You have 9 months until the MVP deadline.

You cannot do a 3-month redesign AND build all features in time.

You have three options:

(1) Amsterdam adapts the design to fit the current architecture.

Risk: the user experience becomes significantly worse.

(2) Bangalore does the redesign. Sprint 1-6 produce almost nothing

visible, putting the 9-month deadline at serious risk.

(3) Ship the MVP with the weaker UX (option 1), then redesign

after the pilot customer has seen it.

- Which do you choose?

- I would choose option (3): Ship the MVP with the weaker UX (option 1), then redesign after the pilot customer has seen it.
This avoids jeopardizing the entire timeline and ensures a base product is delivered, allowing for iterative improvements based on user feedback.

- Who has the authority to make this call - and what happens if

- The authority to make this call should ideally lie with the Product Manager, in consultation with the CEOs from Amsterdam, Bangalore, and Austin. They should consider user experience alongside time-to-market.

- Amsterdam and Bangalore cannot agree?

- If Amsterdam and Bangalore cannot agree, it’s crucial to implement a decision-making framework that allows a designated product owner to make trade-off decisions based on business priorities and technical feasibility.

SITUATION B - THE ONLY MEETING SLOT

You have exactly one 90-minute slot per week where all three teams

can meet synchronously (15:00-16:30 Amsterdam time).

This week you have three agenda items that are all critical:

(1) Finalise the data model - Bangalore is blocked without this.

(2) Review 6 new requirements from the university - Austin needs

a decision before the next customer call on Friday.

(3) Resolve the Amsterdam/Bangalore architecture conflict

from Situation A - it has been unresolved for 2 weeks.

You can cover two of the three properly in 90 minutes.

- Which item do you drop from the live meeting?

- I would drop item (3): Resolve the Amsterdam/Bangalore architecture conflict.
Given the urgency of getting the data model finalized and reviewing requirements from the university, resolving the ongoing architecture conflict can be addressed offline through dedicated meetings between the two teams later.

- How do you handle it differently so it does not stall the team?

- To handle it differently, I would suggest a smaller synchronous meeting just between Amsterdam and Bangalore to tackle the architecture issue, while ensuring outcomes from this meeting are communicated back to the larger team in subsequent sessions.

SITUATION C - THE LEGAL BLOCKER

Halfway through Sprint 3, Austin calls with urgent news:

the University of Texas legal team has blocked all student data

collection until a FERPA (Family Educational Rights and Privacy Act)

compliance agreement is signed. Signing takes 6-8 weeks minimum.

Bangalore is currently mid-sprint, building the recommendation engine

that depends entirely on that student data.

You have three options:

(1) Stop Bangalore's work immediately. Wait 6-8 weeks.

Cost: 6-8 weeks of lost development time and team frustration.

(2) Continue building the engine on synthetic (fake) data.

Risk: the engine may need significant rework once real data arrives

and behaves differently than expected.

(3) Redirect Bangalore to a different part of the product

(e.g., the LMS integration) while legal is resolved.

Risk: context switching costs and the engine falls further behind.

- Which option do you choose?

- I would choose option (2): Continue building the engine on synthetic (fake) data.
This allows progress to be made while ensuring team momentum is maintained, even though there’s an acknowledgment of the risk involved with potentially needing rework later.

- How do you communicate this decision to the Bangalore team?

- I'd communicate this decision to the Bangalore team with clarity and transparency, framing it as a necessary step to maintain progress and empowering them to innovate with synthetic data while making it clear that adjustments might be needed when real data becomes available.

### TASK 3 - REFLECT

In 2-3 sentences:

- Which situation revealed the biggest structural weakness in how LearnLoop is organised?

- The situation revealing the biggest structural weakness in how the company is organized is the incoherent prioritization and communication of requirements across the distributed teams. This leads to misalignment and inefficiencies.

- What would need to change in the company to make that situation not happen in the first place?

- To prevent this from happening in the first place, a centralized, ongoing stakeholder engagement process should be established to ensure all teams can align on priorities, requirements, and expectations regularly.

### EXTRA TASK – RATE

Rate the reflexionbot in 2-3sentences:

It was very easy to get the detailed answers from the bot. I only copied the Tasks from word an put the text in the ChatBot an he gaves me the solutions.